## ICD-11 Roadmap - Timeline
The ICD-11 Decision Roadmap Timeline outlines activities that will need to be undertaken to assess the ICD-11 for Australian use.
ICD-11 Decision Roadmap - Timeline |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | Report of ICD-11 Roadmap Activities | 2026
[12 empty] | Final synthesis |  |  | Decision
No. | Task | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4
1.1 | Establish ICD-11 Taskforce and Governance | Convening of AITF |  |  |  | Extension to monitor and facilitate Roadmap activity progress
3.3 | Terminology Mapping
3.4 | ICD-11 Classification Preparation
3.1 | Mapping and Dual Coding Studies
1.4 | International Engagement |  |  | Develop Strategy |  |  | Conduct strategy
2.1 | Identify Indicators Current Use of ICD-10-AM
2.2 | Identify Indicators Potential Use of ICD-11
2.3 | Health Data Gap Identification
5.1,5.2 | Assess and Identify IT Impacts and Systems Infrastructure
1.2 | Identification of Australian Stakeholder Groups and Use Cases
6.2 | Education Needs Assessment
4.1 | Communications Strategy |  |  |  |  | Develop strategy |  |  |  | Conduct strategy
1.3 | Identification of WHO Resources
3.2 | Assessment of Alternative Classifications
2.4 | Data Collection Method Assessment
6.1 | Workforce Strategy
2.5 | Assess Broader System Enhancements
1.5 | Implementation Costings Analysis